## Sheet1
The same categories as risks and early warnings
Project ID | Date Raised | Category | Issue Title | Description and Impact | Status | Cost | Mitigation | Action by Date | Owner
543341 | 2019-10-24 | Technical | Delivery of Units | Reputational damage implicated when units not achieved. | Open | 12391 | Managed through commZZCee reports and press releases by ZTMand IINC. | 2022-12-31 | Mikayla Downs
543341 | 2019-10-29 | Technical | Client Resource | Lack of Client resource and not skill set, results in delayed response of responding to their actions and increase delay and cost to Programme | Open | 8868 | ZTMresource their slowing rates | 2019-12-31 | Aryana Fitzpatrick
543341 | 2019-11-04 | Legal | Legal Resources | Lack of legal resource results in contract award dates not being achieved, thus resulting in a delayed start. | Closed | 2325 | ZTMto appoint dedicated person and point of escalation to have legal matters dealt with as priority. | 2019-12-01 | Mikayla Vaughn
543341 | 2019-10-30 | Commercial Risks | Delivery Resource | Client delivery resource are not aligned with the Programme Vision and strategic priorities, thus nullifying conflict in ideas | Open | 6396 | The approved blueprint will detail all processes and should be read by everyone involved in the programme and complied with at all times. | 2020-01-01 | Aryana Fitzpatrick
543341 | 2019-10-27 | Technical | Resource | Lack of legal resource to advise on Developers ZZC - financial model | Open | 1064 |  | 2019-12-01 | Alexis Herrera
346321 | 2019-11-02 | Commercial Risks | Budget | Reduction in units on all direct sites will increase pressure on resources. | Open | 11860 |  | 2022-01-01 | Mikayla Downs
346321 | 2019-11-02 | Legal | BUW funding | HAG funding applications can only be made for units completed. None of the projects are programmed to have units completed by this date. | Open | 11335 |  | 2020-01-01 | Alexis Herrera
346321 | 2019-11-09 | Technical | Delayed site entry for Contractor |  | Closed | 1000 |  | 2022-12-31 | Mikayla Vaughn
346321 | 2019-10-20 | Legal | Incorporation of MHP and roof | Additional costs incurred should these be signed off. | Closed | 32400 | Full review of proposals submZZCed by PKS. | 2019-12-31 | Madelyn Davila
678426 | 2019-11-03 | Legal | Specification is defined and won't align with programme subsequently tendered |  | Open | 300 |  | 2019-12-01 | Aryana Fitzpatrick
678426 | 2019-10-22 | Commercial Risks | Construction works have started and no Employers Agent in place |  | Open | 12200 |  | 2020-01-01 | Mikayla Vaughn
678426 | 2019-11-04 | Technical | Scope of works to Ave | Scope is yet to be defined as resurfacing is not currently included. | Open | 7000 |  | 2019-12-01 | Mikayla Vaughn
678426 | 2019-11-07 | Technical | Additional ground works | Additional works to be undertaken and unchartered services have been identified on site | Closed | 4000 |  | 2022-01-01 | Mikayla Vaughn