## General Risk Register
Likelihood * Impact = Risk Score Risk Score: 1-7 GREEN, 8-15 AMBER, 16 - 25 RED If there is no action data it means risk is not yet mitigated The same categories as Early Warnings and issues The postmitigated cost includes premitigated cost
Project ID | Date Raised | Category | Risk Title | Threat/Opportunity | Risk Description | Effect of Risk | Project Stage | Status | Likelihood | Impact | Risk Score | Cost | Risk Control Measures | Action by Date | Mitigated Likelihood | Mitigated Impact | Mitigated Risk Score | Mitigated Cost | Owner
543341 | 2019-10-28 | Technical | ACM | Threat | Further volumes of ACMs could be detected. | Health implications to those working with/area of the site. Reputational damage for KOL. | 5 | Closed | 4 | 5 | 20 | 6356 | Low level of ACMs identified, KOL H&S advisor has not identified any definitive legislation for use of material. Fairhurst have developed strategy for use. | 2019-12-13 | 3 | 5 | 15 | 15046 | Tyson Santiago
543341 | 2019-10-28 | Legal | Potential exposure to asbestos in excess of the levels anticipated – workforce and members of the public. | Threat | Potential health impact for those in the area of the site, or working on the site. | Health implications, reputational damage. | 5 | Closed | 4 | 5 | 20 | 5718 | Contractor to follow RAMS and report if material visibly identified. | 2019-12-06 | 2 | 3 | 6 | 11342 | Tyson Santiago
543341 | 2019-10-28 | Commercial Risks | Earthwork strategy | Threat | KLOSmay have insufficient detail contained within Earthwork strategy including the use of stockpile materials that contain asbestos. | Delay to KLOSstarting on site. | 5 | Closed | 4 | 4 | 16 | 2571 | Fairhurst design w/c 4th October will ensure efficient use of material to minimise waste offsite and use the contaminated material safely. | 2020-02-06 | 2 | 2 | 16 | 11869 | Mikayla Vaughn
543341 | 2019-10-28 | Technical | Heat & Power delivery of MONH offsite. | Threat | MONH offsite construction programme to be developed and align with ACW's programme of works.CV+K /KOL have no input to manage Heat and Power works, this increases the risk. MONH may experience issues during installation that may impact KLOSprogramme. | Impact on KOL Edinburgh Programme out with KWC's control. | 5 | Closed | 3 | 5 | 15 | 12096 | Workshops being held between design team and KLOSto progress design timeously. | 2020-01-30 | 3 | 3 | 9 | 21282 | Aryana Fitzpatrick
543341 | 2019-10-28 | Commercial Risks | Completion date for offsite culvert works | Threat | KLOShave previously advised of a delay to the completion date of the offsite culvert works. | Delay to programme/ EoT claim | 5 | Closed | 4 | 3 | 12 | 991 | Monitor progress and prompt response to TQ's. | 2019-12-03 | 4 | 3 | 12 | 7434 | Alexis Herrera
678426 | 2019-10-28 | Technical | Plant and vehicle movements, including site deliveries through a residential area and nearby school and nursery. | Threat | Risk of plant being left onsite over night. Large vehicles moving during school hours. | Health & Safety incidents more likely to occur | 5 | Open | 3 | 4 | 12 | 3373 | Ensure areas of movement are contained and appropriate signage in place. Limit deliveries to site to evenings and weekends where possible. | 2020-02-17 | 2 | 2 | 4 | 9227 | Madelyn Davila
678426 | 2019-10-28 | Legal | Unidentified/ unchartered services. | Threat | Risk of unchartered services being identified on the site | May delay KLOSand/ or sectional completion dates | 5 | Open | 3 | 4 | 12 | 3154 | Contractor to highlight unchartered services | 2019-12-30 | 2 | 3 | 6 | 12561 | Charity Gutierrez
678426 | 2019-11-26 | Technical | Phased parking | Threat | 10% of the units are completed, then 10% of the approved parking spaces should be available prior to occupation of those units. ACWs current proposed programme does not comply with this planning condition. | KLOSmay have to re sequence works/delayed KOLess to units | 5 | Open | 3 | 4 | 12 | 11951 | KLOSare reviewing programme | 2020-01-23 | 2 | 3 | 6 | 20894 | Litzy Ross
678426 | 2019-11-26 | Technical | Timber Kit TQ's | Threat | Design team are currently responding to TQ's required by the timber kit sub-contractor. The sub-contractor requires all responses by 27/11/2019 | Impact on KOL Edinburgh Programme out with ACW's control. | 5 | Open | 3 | 4 | 12 | 7284 | Timber-kit sub-contractor has sent detailed email stating all information required. | 2020-01-31 | 2 | 4 | 8 | 16914 | Elisa Jenkins
678426 | 2019-10-28 | Legal | Unforeseen ground conditions | Threat | The site is a brown field site, therefore there is a chance KLOScould encounter unforeseen ground conditions. | Increase in cost. | 5 | Closed | 3 | 3 | 9 | 14046 | KLOSto report as they encounter unforeseen ground conditions. |  |  |  | 0 |  | Kasen Archer
678426 | 2019-10-28 | Legal | Technical Query response times | Threat | TQ's are not responded to, by design team in a timely manner. | KWC's programme is delayed due to lack of information provided by Design Team. | 5 | Closed | 3 | 3 | 9 | 12953 | IINC to monitor TQ response time and chase for responses. Fortnightly design team meetings will highlight urgent technical queries. | 2020-01-30 | 2 | 2 | 4 | 21534 | Kira Watson
543341 | 2019-10-28 | Commercial Risks | Contractor Progress | Threat | Post tender KLOSprogramme showed an extended duration of 4 weeks. | Delay to completion date | 5 | Closed | 2 | 4 | 8 | 2368 | KLOShave provided revised programme taking cognisance of earthworks strategy. | 2020-02-25 | 2 | 4 | 8 | 9186 | Mattie Jenkins
543341 | 2019-10-28 | Legal | Late changes to design introduced by KOL | Threat | Late changes from KOL may add cost and delay programme | Impact start dates and programme | 5 | Closed | 2 | 4 | 8 | 9443 | Late/evolving client changes during RIBA Stage 5-6 to be monitored. | 2020-02-22 | 2 | 4 | 8 | 15691 | Mikayla Vaughn
543341 | 2019-10-28 | Legal | Heat & Power delivery of MONH | Threat | Detailed design and costs not provided by Heat and Power for provision of MONH. | Delay KLOSdelivery until detailed design concluded. Impact SAP calculations | 5 | Closed | 2 | 3 | 6 | 5168 | Workshops being held between design team, progress design timeously. | 2019-12-28 | 2 | 2 | 4 | 11290 | Aryana Fitzpatrick
543341 | 2019-10-28 | Commercial Risks | Mild winter | Opportunity | May KOLelerate building on site. | Moderate temperatures may allow site activities to progress | 5 | Open | 2 | 3 | 6 | 11576 | Forecast for moderate winter in 2019 at this time | 2019-12-20 | 2 | 3 | 6 | 17028 | Aryana Fitzpatrick
543341 | 2019-10-28 | Legal | Systems | Threat | A new communication system is being used for the project (SharePoint). | Information or 'reply by' dates are missed or team members fail to use the system efficiently. | 5 | Closed | 2 | 3 | 6 | 7796 | Training to be provided details of how to utilise SharePoint. IINC to monitor usage and lead by example. |  |  |  | 0 |  | Aryana Fitzpatrick
346321 | 2019-10-28 | Commercial Risks | Landscape requirements | Opportunity | KOL are investigating ways of reducing green space maintenance cost. | Increase / reduce the cost of ACWs works but reduce long term cost to KOL | 5 | Closed | 3 | 2 | 6 | 9049 | KOL to provide details of changes required following workshop. |  |  |  | 0 |  | Mikayla Downs
346321 | 2019-10-28 | Legal | RCC approval requires revised bellmouth | Threat | Instruction to proceed with Bellmouth is issued late. | Delay to CREXcommencing formation of site entrance on site. | 5 | Closed | 3 | 2 | 6 | 10806 | Fairhurst to provide updated Bellmouth drawing/ co-ordinates ASAP. |  |  |  | 0 |  | Madelyn Davila
346321 | 2019-10-28 | Technical | Utilities Quotations | Threat/Opportunity | Utilities quotes are to be refreshed, the cost might have increased since the original quotation was received. | Change to cost | 5 | Closed | 3 | 2 | 6 | 4464 | Utilities quotations are currently being refreshed. Review opportunity / risk again when new quotations received. |  |  |  | 0 |  | Mikayla Downs
346321 | 2019-10-28 | Commercial Risks | Delay to Statutory Approvals | Threat | Delayed responses from statutory bodies may delay programme | May delay CREXand/ or sectional completion dates | 5 | Open | 2 | 3 | 6 | 12575 | Maintaining regular liaison with Building Control, Planning and Roads Dept. | 2019-12-04 | 2 | 2 | 4 | 21811 | Litzy Ross
346321 | 2019-10-28 | Technical | Neighbours complaints | Threat | The site location is in a dense residential area in close proximity to construction activities. There is a chance of neighbours raising nuisance complaints i.e. noise, dust and vibration. | Potential reputational damage to KOL. | 5 | Open | 3 | 1 | 3 | 2016 | Inform neighbours of progress on site and provide advance notice of noisy works. | 2020-01-04 | 1 | 2 | 2 | 8381 | Aryana Fitzpatrick
346321 | 2019-10-28 | Commercial Risks | Site Security | Threat | The site is located in a densely populated residential social housing area. | Safety and reputational damage. | 5 | Open | 3 | 1 | 3 | 1839 | Ensure site security systems are maintained and reviewed as works progress. |  |  |  | 0 |  | Litzy Ross